AUCOOP · Hospital Digitalisation Handbook · Instrument B-2

Level decision

Before you go   ·   Complete after B-1, before any equipment is bought

Decide how far up the tool spectrum this deployment goes — driven by what the hospital can sustain after you leave, not by need.

| Hospital | Unit / area | Completed by | Date |
| --- | --- | --- | --- |

1. The four conditions — tick every condition that HOLDS

From the implementation matrix (thesis §6.3.1). None holds: level 1 or 2. Conditions 1 and 2: level 3. All four: level 4, phase by phase. If a condition needed for the planned level does not hold, drop a level or do not deploy.

☐  1. A person employed by the hospital is responsible for the system and can be reached after we leave  — a name and a role — not 'someone will look after it'

☐  2. Protected power and a working network at the point of use, verified in each unit  — verified by us, in the room, with a device

☐  3. A management mandate: a named owner, and agreement to close the paper registers when the exit criteria are met  — an administrator's enthusiasm is not the same authority

☐  4. A paper process that can actually be retired, including the statutory returns that depend on it  — if paper continues alongside, nothing has been digitised

☐  Who pays the running costs — connectivity, spares, batteries, support — is agreed  — not a level condition, but agree it before anything is bought

2. The tool spectrum

| Level | Scope | Tools | When |
| --- | --- | --- | --- |
| 1 | Data collection & surveys | KoBoToolbox, ODK | None of the four conditions holds |
| 2 | Aggregate reporting & case tracking | DHIS2, CommCare | None holds; a reporting officer; national alignment |
| 3 | Clinical record | OpenMRS | Conditions 1 and 2 hold |
| 4 | Full HIS — clinical, lab, pharmacy, billing | Bahmni, GNU Health | All four hold — then phase by phase |

3. Decision

| Level chosen (1–4, or 'do not deploy') | B-1 total score | Decided by (names) | Date |
| --- | --- | --- | --- |

Justification — why this level and not the one above:

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

If we deploy below what was hoped: what has to become true for next year's answer to be higher?

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

That last line is a prediction with a date on it. Next year's team is asked whether it came true — so write something that can be checked.

4. Stop-rule override — complete this ONLY if a condition needed for the chosen level does NOT hold and you are deploying anyway

This is the most important section on the form. In 2026 at Lunsar a level-4 system was deployed before protected power had been verified in every unit, by careful engineers with reasons that were never written down. An override is sometimes right. An unrecorded override is how a decision becomes invisible to everyone who comes after.

| Which conditions did not hold | Deploying anyway? | Decided by (names, roles) | Date |
| --- | --- | --- | --- |
|  | Yes / No |  |  |

On what grounds — the actual reasoning, not the conclusion:

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

What is being put in place to compensate, and who is accountable for it:

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

What would have to be true for us to reverse this decision, and who reviews it:

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________