AUCOOP · Hospital Digitalisation Handbook · Instrument D-4

Phase exit gate

While you are there   ·   At the end of each phase

A phase is not finished because the feature works. Complete one sheet per phase you claim to have closed.

| Hospital | Unit / area | Completed by | Date |
| --- | --- | --- | --- |

Phase being closed

| Phase (1–4) | Name | Claimed closed on | By |
| --- | --- | --- | --- |

1. Exit criteria — every phase (implementation matrix)

No fixed duration. The anchor: the phase's reports match the paper counts over one complete reporting cycle. Criteria not yet verified when the team leaves are assessed by the owner and reported remotely.

| Dimension | Criterion | Met? (Y/N/later) | Evidence / who confirmed |
| --- | --- | --- | --- |
| Technical | Available during working hours; any outage covered by the emergency paper forms |  |  |
| Functional | Every encounter recorded in the system; reports match paper counts for one full reporting cycle |  |  |
| Motivational | Staff enter the data themselves, without the team present |  |  |
| Governance | Owner confirms; paper registers closed and archived; paper kept only as emergency backup |  |  |

1b. Engineering conditions — evidence for each

| Condition | Met? (Y/N) | Evidence (what was shown, to whom) |
| --- | --- | --- |
| Phase-specific gate (see handbook D-4 table) |  |  |
| Works offline-tolerantly — degrades sensibly when power or network fails |  |  |
| A hospital-usable runbook exists, written for zero prior IT experience |  |  |
| The runbook was tested on someone who was NOT in the training |  |  |

2. The four measured outcomes

Use these definitions exactly — S-1 re-measures the same four at six and twelve months, and a measure whose definition changes between cohorts cannot be compared across them. Write the denominator, not just the ratio.

| Outcome | Definition — use exactly this | Numerator | Denominator | Value |
| --- | --- | --- | --- | --- |
| Adoption | Eligible staff who used it in a normal week ÷ eligible staff |  |  |  |
| Fidelity | Records entered at the point of care ÷ records entered (sample one real day) |  |  |  |
| Penetration | Units live ÷ units in scope at handover (name them) |  |  |  |
| Sustainability | Running, with a named owner in post, on this date |  |  |  |

3. The other four — one sentence each, in prose

These will not be measured honestly in the last week of a three-week deployment. A form that returns three real numbers and five guesses produces something that looks like data. Write a sentence.

| Outcome | The question | What you observed |
| --- | --- | --- |
| Acceptability | Do staff find it agreeable? |  |
| Appropriateness | Does it fit this setting? |  |
| Feasibility | Can it be done here, with these people? |  |
| Implementation cost | Hardware, travel, staff time, recurrent |  |

4. Six- and twelve-month check

Sustainability is not measurable at departure — it is measurable in a year. Name the person and the dates here, and again in L-1 section 4. They will be filling in S-1.

| Who checks | 6-month date | 12-month date | Contact route that will still work then |
| --- | --- | --- | --- |

5. What was not done

What was NOT done in this phase, and why (the next team's scope starts here):

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________