AUCOOP · Hospital Digitalisation Handbook · Instrument L-1

Handover pack — cover sheet

Before you leave   ·   Started on Wednesday of week two; complete before the last day

What physically stays at the hospital. Started mid-second-week, walked through with the named owner in person before departure.

| Hospital | Unit / area | Completed by | Date |
| --- | --- | --- | --- |

1. Named owner

| Name | Role | Contact | Walked through the pack on (date) |
| --- | --- | --- | --- |

2. Contents — tick when present and handed over

☐  Runbook per deployed unit  — daily task, screenshots, written for zero prior IT; tested on someone not in the training

☐  'What to do when it breaks' sheet  — the five most likely failures and the first thing to try; includes 'the system takes 3–12 minutes to start'

☐  Credentials handed over securely  — in person, separately, recorded for rotation — NEVER written in this pack

☐  Support escalation ladder  — tier 0 in-product help · tier 1 hospital IT staff and super-users · tier 2 our organisation, remotely · tier 3 contracted implementer, if funded

☐  Encryption key and credentials held by the hospital's owner  — not by a departing volunteer; without the key the backups cannot be restored

☐  Downtime procedure written, emergency forms stocked in every unit, rehearsed  — at least 8 hours of forms per unit; who declares downtime; how paper is entered afterwards

☐  Battery replacement date  — from the room temperature; who budgets it

☐  Backup demonstrated by the owner while we watched  — backup AND restore

☐  Cutover plan, if paper is retired after departure  — date, who announces it, what happens on the day

☐  Who checks it at 6 and 12 months  — name and date

☐  What we deliberately did NOT do, and why  — the most useful page in the pack

☐  The handbook version we followed  — v0.5

3. Support ladder

| Tier | What | Name | Route (phone / email / where) |
| --- | --- | --- | --- |
| 0 | Self-help in the product | — |  |
| 1 | Hospital IT staff and super-users |  |  |
| 2 | Our organisation, remotely (VPN) |  |  |
| 3 | Contracted implementer (SLA), if funded |  |  |

4. Six- and twelve-month check

| Check | Who | Date planned | Done? Result |
| --- | --- | --- | --- |
| 6 months |  |  |  |
| 12 months |  |  |  |

What we did not do, and why:

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________