AUCOOP · Hospital Digitalisation Handbook · Instrument S-1

Six- and twelve-month check

Six and twelve months later   ·   At six months and again at twelve months, on the dates written in L-1

Did it survive? The only instrument completed after the team has gone home — and the only one that measures an outcome rather than an intervention. Ten minutes, remotely, by the person named in L-1 section 4.

| Hospital | Unit / area | Completed by | Date |
| --- | --- | --- | --- |

Designed to be answerable from one conversation with the super-user, by phone or messaging. You are not auditing anyone. A blank field is a finding; an invented one is worse than nothing.

1. Which check is this

| Check | Deployment it follows (site, dates) | Handbook version that deployment followed | Answered by, and how reached |
| --- | --- | --- | --- |
| ☐ 6 months ☐ 12 months |  |  |  |

2. Is it running

| Question | Answer | How you know |
| --- | --- | --- |
| Is the system reachable / running at all? | Yes / No / Partly |  |
| Units live now, out of the units handed over | / |  |
| Who is using it — roles and roughly how many people |  |  |
| Is it used at the point of care, or entered later from paper? | Point of care / Batched / Both |  |

3. Paper

The handbook's central design rule is that a process moves only when the digital path is the ONLY path. This is where you find out whether it stayed that way.

| Process retired at handover (name it) | Still retired? | If it came back — when, and what triggered it |
| --- | --- | --- |

4. The owner

| Question | Answer |
| --- | --- |
| Is the named owner from L-1 still in post? | Yes / No — if no, who now? |
| Is the post funded, and by whom? |  |
| Are the super-users still in place, and do they still have the time allowance? |  |
| Has anyone at the hospital been paid, in the period, for work on this system? |  |

5. What broke since we left

Including anything that broke and was NOT fixed. Silent downtime is the failure mode this project has repeatedly missed — a remote check in February 2026 found a server inactive and there is no record of what happened next.

| What happened | Roughly when | Who dealt with it | How long was it down? | Did they need outside help? |
| --- | --- | --- | --- | --- |

6. B-1 re-scored — the same seven dimensions, today

Score exactly as in B-1, 0 (no gap) to 10 (total gap), against the same anchors. The point is the movement, not the number: a gap that has not closed is the finding.

| Dimension | Score at B-1 (before travel) | Score at departure (D-4) | Score today | What moved, or why nothing did |
| --- | --- | --- | --- | --- |
| Information |  |  |  |  |
| Technology |  |  |  |  |
| Processes |  |  |  |  |
| Objectives & values |  |  |  |  |
| Staffing & skills |  |  |  |  |
| Management systems |  |  |  |  |
| Other resources |  |  |  |  |
| TOTAL |  |  |  |  |

7. The four outcomes, now

The same four as D-4, measured the same way. If you cannot measure one from here, write 'not measurable remotely' — that is itself worth knowing about the measure.

| Outcome | Definition used | Value at departure | Value now |
| --- | --- | --- | --- |
| Adoption | Eligible staff using it in a normal week ÷ eligible staff |  |  |
| Fidelity | Records entered at the point of care ÷ records entered |  |  |
| Penetration | Units live ÷ units in scope at handover |  |  |
| Sustainability | Running, with a named owner in post, on this date |  |  |

8. What the hospital wants that it is not getting

In their words. This is the next deployment's requirements list, gathered a year early and for free:

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

____________________________________________________________________________________________

9. Where this goes

☐  Filed with the deployment's other completed instruments  — same folder, same naming convention

☐  Sent to whoever merges the A-1 returns  — if that role is still unnamed, send it to the handbook repository as an issue

☐  The next check is scheduled  — 12-month check booked now, with a name and a date — or, at 12 months, closed

| Next check due | Who will do it | Contact route that will still work then |
| --- | --- | --- |